## I873 Action Tracking
TP_i873# | Status | ViTel Net Tracking Comments | Issue Headline | Issue Description | Resolution | issue origin | Priority
#1 | Completed | Bring the P138 release application to the latest development stage before proceeding with new development (Note: P138 release application source code was excessively simplified by release date) | Make detailed analysis of TP RPCs (routine/entry point) to VIX pathology web services and check which web services are in use by the Client application. | Detailed mapping needs to be established between all MAGTP RPC-s (used/unused) to VIX Pathology web services (have not found it in P138 documentation). After detailed analysis, appropriate client application source code needs to be uncommented to get to the application code base that was more advanced then the release version. | Used P138 release source code (M, VIX/java, Client Apps/C#) and the latest code base that was retrieved from the VA's source code control system(s): 1. Made diff on (release and latest development) M routines, and compiled the ultimate i873 candidate for each case. 2.After careful Client code (C#) analysis, all relevant commented code segments were uncommented (gradually) to maintain functional integrity between the persitance (M code), the bussiness (VIX/java) and the presentation (C#) layers. 3. At each functional change functional integrity tests were performed. [4.] Ocasionally, the revealed and suggested changes were presented to VA SME-s and their continuous TP Workflow feedback drove the entire i873 project. | Patch 138 | 1
#2 | Completed | The TP WL Manager application times out prematurely. | No matter what timeout settings are configured in the TP Configurator application, The TP WL Manager aplication times out in 15-30 seconds. |  | Using the "new style" RPCBroker fixed the problem, no more VIX induced timeouts occur. /VIX/ | Patch 138 | 1
#3 | Completed | On Client app startup "class not registered" shows up | ~ | Bahavior shows only while in Visual Studio Debug | Adjusted project settings resolved the issue. | Patch 138 | 2
#4 | Completed | WL Configurator has window flashing before startup |  |  | login before showing main window /C#/ | Patch 138 | 2
#5-#6 | Completed | Make the latest KIDS package for the i873 project, so more than one site can be maintained | Before going further, make an M KIDS package that reflects the unreducted P138 intent. | ~ | #5: MAG3_0P873T3.KID was made #6: KIDS package used to populate changes on other simulated test sites | Innovation 873 | 2
#7 | Completed | CPT Code table is not reachable | Error with Imaging service account | pathology/fields/506/location/00111 ==> "Could not find any location that matches the description." -> Needed CPT code table# hit for some other URL buzzword in place of location | VIX changed: now using pathology/fields/506/cpt/<searchstring> /VIX; C# code adjusted accordingly/ | Patch 138 | 1
#8 | Completed | Q to SME-s: View Report button is for viewing a Verified (Completed) Report -- Should we rename button? | ~ | ~ | SME-s: Not relevant, keep as it is! Resolved (not needed) | Innovation 873 | 3
#9 | Completed | I873 Documentation by 9/14/15 | A. Test Plan, RTM, Test Scripts done. B. SRS, SDD updates needed. C. New Install Manual, Release Notes and Technical Manual needed. D. User Manuals | I873 changes should be reflected in every existing TP WL document and new ones are due by 9/14/15 | A. Done B. Done C. Done D. Done | Innovation 873 | 1
#10 | Completed | Setup environment for I873 testers on a VM | ~ | For i873 independent tester accounts are desired. | The same M development accounts can be used with time-sharing. /New Windows users are created for testers/ | Innovation 873 | 3
#11 | Completed | Patient tab should appear between Unread and Read tabs, like in SDD | ~ | ~ | C# code uncommented. | Patch 138 | 1
#12 | Completed | Auto sign-on performance issue (related to CCOW and port locking) | The TP user has to sign in again upon a longer system induced timeout /without losing context/. | host<>IP name resolution; new vs. old style broker in message format in the VIX | DNS or host file update; Updated VIX code | Patch 138 | 2
#13 | Completed | "About" window needs to be updated for i873 | ~ | ~ | "VistA Innovation 873" replaced "Silver Spring, OIFO" i873 replaced P138 /C#/ | Innovation 873 | 1
#14 | Completed | Consult request button click does not return consulting site (list) | ~ | ~ | FIXED by configuration set right (Resolved) | Innovation 873 | 1
#15 | Completed | Referal site Edit Report returns partially filled template, no Sup. Reports, no Snomed/CPT info | ~ | ~ | FIXED by configuration set right (Resolved) | Innovation 873 | 1
#16 | Completed | Referal site Notes button returns no note | ~ | ~ | FIXED by configuration set right (Resolved) | Innovation 873 | 1
#17 | Completed | Get a VistA patch # | ~ | ~ | NOT A National release, just an innovation project, keep i873 (resolved) | Innovation 873 | 2
#18 | Completed | Result and Consult status columns are missing... | ~ | ~ | uncommented entries in WorklistView.XAML | Innovation 873 | 1
#19 | Completed | Make sure all of the involved site's cases are returned | ~ | ~ | uncommented code /C#/ | Patch 138 | 1
#20 | Completed | Pending consult does not show --> No ability to delete a Pending or cancelled consult | ~ | ~ | see #28! /VIX/ | Innovation 873 | 1
#21 | Completed | Create release code | ~ | ~ | Had to set 32 bit mode for 64 bit platforms because CCOWBroker.dll (C++) module was 32 bit | Innovation 873 | 1
#22 | Completed | WLMgr main screen format needs adjustments not to clip content with scrollbars | ~ | ~ | fixed width settings in .XAML file /C#/ | Patch 138 | 1
#23 | Completed | Failure message on Main Report Verify | ~ | ~ | see #24! | Innovation 873 | 1
#24 | Completed | VIX reconnect issue to vix (intermittent long delays) | ~ | ~ | port 8443 needed to be opened on the VM used to run VIX | Innovation 873 | 1
#25 | Completed | Released items do not show on the Read list | ~ | MAG PATH CASELIST reportStatus(U,R,C) is not set at all -- comprehensive Lab report verified workflow must be implemented… | CASE status is set on Report Verified(Released) now /M/ | Innovation 873 | 1
#26 | Completed | (Un)Reserved non-local item falls off the list until Refresh | ~ | ~ | introducing save/restore selected item on list logic for all commands /C#/ | Patch 138 | 1
#27 | Completed | Filter naming, menu differ from button |  |  | Filter create pop up fixed (XAML file fix) /C#/ | Patch 138 | 1
#28 | Completed | consult status is always blank on WLMgr. | no CaseConsultationURN was returned to remote client | ~ | Corrected the getting case interp./consult entries from a remote site in the VIX2VIX scenario. /VIX/ | Innovation 873 | 1
#29 | Completed | Should not be able to edit report from patient list | ~ | ~ | disabled edit report button in Patient tab /C#/ | Patch 138 | 1
#30 | Completed | Ability to send an Hl7 order message only if a consultation requested (not all the time). | ~ | ~ | indirectly Fixed by asking for vendor filtering in API (Resolved) | Innovation 873 | 2
#31 | Completed | Consult status column is not updated | ~ | MAG CHANGE CON STATUS (pathology/case/consultation/{caseConsultationId}/{status} -- post) does nothing --> no workflow | see #28! /VIX/ | Innovation 873 | 1
#32 | Completed | TP support tables are never purged in M | ~ | ~ | Not a high priority according to M /OS/ space management (DB growth is miniscule…) -- Resolved | Patch 138 | 2
#33 | Completed | View Image integration -- for Aperio | ~ | ~ | 1. implement Aperio ImageScope sample file -- sample slides .sis file hooked, popped up on view 2. then HL7 messaging established with Aperio and on ORU^R01 reception in MAG PATH CASELIST Case's Slides Available flag and Number of Images fields are autoadjusted MAGTP GET SLIDES INFO / GETSD^MAGTP015 added {../pathology/case/slidesinfo/{caseId} -- get} /M, VIX-java, C#/ | Innovation 873 | 1
#34 | Completed | View in Capture is commented, do we need it? | ~ | ~ | see 33 -- vendor integration; no own viewer/snapshot is needed! (resolved) | Innovation 873 | 2
#35 | Completed | not getting CPT codes for any SP case | ~ | ~ | Besolved by M adjustments (configuring lab package correctly): 1. Turned WLOAD STATS on 2. Site settings for referal and consulting sites were fixed 3. Added appropriate CPT (workload) codes to a case only when SP & CY Reporting verified; called in PUTFIELD^MAGTP001 on .11 (Released Date) set | Innovation 873 | 1
#36 | Completed | After report Verify and closing Edit Report item stays on the Unread list until Refresh. | ~ | ~ | Added EDIT^MAGT7MA call (set case item status Read) to verify date setting report field update. Also see #38 /M/ | Innovation 873 | 1
#37 | Completed | TIUPREP^LRAPRES and STORE^LRAPRES calls are missing for GUI Main Report Verify (when release date set). | ~ | ~ | added missing calls to MAGTP PUT REPORT FIELD on Report Relase /M/ | Innovation 873 | 1
#38 | Completed | issue 1: restoring focus on selected item of the list. 2. periodic refresh is a must (every 1-5 sec) | ~ | ~ | Tweaking tree control of client app for both issues, (periodic refresh in hardcoded 3 sec) /C#/ | Innovation 873 | 1
#39 | Completed | SR copy case (to consulting site) bug after saving SR is followed by a Consult status update /to Completed/ on reading site. | ~ | ~ | Specimen limit set longer then 2-75 char (120) in the field SPECIMEN in SPECIMEN SUB-FIELD in SURGICAL PATHOLOGY SUB-FIELD in file LAB DATA /M/ | Innovation 873 | 1
#40 | Completed | Default the Supplementary report's date to today's date | ~ | ~ | C# change | Innovation 873 | 1
#41 | Completed | Check TP WL MGR for Memory leaks | ~ | ~ | no memory leak&crash found after running app for over a day… | Innovation 873 | 1
#42 | Completed | Test if Main Report Verify fails because of Comment field not added at case creation in Roll & Scroll | ~ | ~ | Negative! | Innovation 873 | 1
#43 | Completed | Make installer for both i873 clients (use P138 ones to start from) | one MSI/EXE for both TP Configurator and TP Worklist Manager with shortcuts on Desktop | P138 used InstallShield 2012 Spring in BASIC MSI mode -- follow it; include resource install (for Aperio now) /vcredist….exe files and registry settings for broker server "host,port" should not be included; they will be detailed in the Installation Guide/ | InstallShield V12 .ism files are created for both -- resulting in .EXE files (tested) | Innovation 873 | 1
#44 | Completed | Refresh makes children entries disappear on WL display. | ~ | ~ | Refresh NOW remembers for all expanded or collapsed cases /C#/ | Innovation 873 | 1
#45 | Completed | Method and Priority columns are missing... | ~ | ~ | uncommented entries in WorklistView.XAML -- /but later SMEs said no one uses them (resolved)/, so went back to commented | Innovation 873 | 2
#46 | Completed | Where should Case fields Method and Priority be set if they are needeed at all? | ~ | ~ | The SME-s said they would not use it (resolved), see #45! | Innovation 873 | 2
#47 | Completed | Shorthands for CPT codes? | ~ | ~ | SITE HAS Shorthands in LAB package (CPT table?); so no change is implemented on Client side (resolved) | Innovation 873 | 2
#48 | Completed | Allow 5-digit Site ID prefix in ACC#. |  |  | Resolved. Note: the site column always shows on the WL next to the ACC#... -- Isn't that an unnecessary duplication? The LAB package is not doing it, might have trouble on functionality as the Lab package composes the case ID from 3 components (AP Section + Year + Acc#) in multiple entries -- if this feature is really needed, do it in HL7 messages only!!! (see with Mirth); business layer should strip it off | Innovation 873 | 2
#49 | Open | Dictation/transcription technology must be supported (Voicebrook -- Voiceover 5?) | ~ | ~ | new keyboard shortcuts? text boxes to rtf?? -- waiting for vendor input… | Innovation 873 | 1
#50 | Completed | Analyze HP Fortify errors over .NET source code | ~ | ~ | Switching to VS2013 and remove special chars '(' and ')' from main folder name. | Innovation 873 | 1
#51 | Completed | Make sure, on context change, viewer application slide stack is emptied if it was not emty! | ~ | ~ | EraseCaseSlides called on case deselction /C#/ | Innovation 873 | 1
#52 | Completed | When adding CPT codes, remember Hospital location typed in at previous time, while in menu. | ~ | ~ | Removed reinitializing last selection /C#/ | Innovation 873 | 1
#53 | Deferred | No ability to delete a coded CPT entry | ~ | ~ | Not in any docs; SMEs said they don't need it (of course Clerks will enter codes, we should ask their opinion ?!) -- Resolved by docs; deferred to extension period | Innovation 873 | 1
#54 | Completed | Make sure case is locked while Editing Report, so other Site/users can't do similar changes on the case | ~ | ~ | Resolved: Users must have distinct DUZs (SSNs) and cannot be LRAPSUPER is the solution; Lock timeout is existing config option in minutes --> LRASUPER key removed from users. | Innovation 873 | 1
#55 | Completed | Log 'reference case creation' event when such message is displayed | ~ | ~ | Checked code, it is logged! | Innovation 873 | 1
#56 | Completed | Try to expand Gross Description section when Edit Report page pops up. | ~ | ~ | Not possible - instead: keep GD on top in WLConfigurator (document in Configurator User Manual!) -- Resolved | Innovation 873 | 1
#57 | Completed | When WL apps start up, they stay in background, keep them on top! | ~ | ~ | Forground activation is requested explicitely. /C#/ | Innovation 873 | 1
#58 | Completed | Patient tab does not show correct image count but 0. | ~ | ~ | Java TranslateLabCase method is adjusted as different structures are returned by RPC calls with similar output /java/ Note: SDD says: From the Patient tab, users can perform: refresh, edit/view report, notes, or view health summaries | Innovation 873 | 1
#59 | Completed | Make Aperio files resource instead of in C:\Temp folder | ~ | ~ | NoSlides.sys is a recource now in PFx86\VistA\Imaging\Telepathology\Vendor\Aperio\ -- installed by installer; see #43 | Innovation 873 | 1
#60 | Completed | If viewer was started by WLMGR, Shutdown ImageScope on WL MGR exit! | ~ | ~ | Explicitely kill ImageScope app on TP WL MGR shutdown, if it was started by the WL MGR /C#/ | Innovation 873 | 1
#61 | Usability | Use <CR> on field entries as relevant button click (various places). | ~ | ~ | … very low priority … | Innovation 873 | 3
#62 | Completed | Remove View Alert sending for SR Verify! (SME request) | ~ | ~ | Done /C#/ | Innovation 873 | 1
#63 | Completed | Change LRSUPER to LRAPSUPER for TP WL users | ~ | ~ | Done in SDD. | Innovation 873 | 1
#64 | Completed | Review Reserve/Unreserve/lock "logic" and apply it foolproof around Edit Report and Requesting Consultation menus | ~ | By the P138 design/implementation, the TP WL MGR app provided only visual reservation notification for other users, but did not prevent them doing concurrent changes on the same case. So the reserve/unreserve functionality can be bundled with the exeisting Lock/Unlock mechanism and the "Reserved By" column can be renamed to "Locked By"! | The following are implemented: 1. (Un)Resreve buttons are removed; 2. Entering Edit Report or Request Consultation reserves after lock, and unreserves before unlock (on exiting the respective menu) 3. LRAPSUPER key should not be given to users just the sysadmin (for forced unlock)... or removed from M locking code (see #54.) 4. On report Lock timeout, while in the Edit Report menu, locking continues (renewed) /C#/ | Innovation 873 | 1
#65 | Completed | Make sure initials are set for all TP (visitor) users (also make sure their SSN is unique --> DUZ unique) | ~ | ~ | Document in Installation Guide! (resolved) | Innovation 873 | 1
#66 | Usability | SNOMED hierarchy should auto expand on adding a new child level | ~ | ~ | low pri | Innovation 873 | 2
#67 | Usability | Worklist column heading names truncated when there is enough width to show the full name. | ~ | ~ | low pri | Innovation 873 | 2
#68 | Completed | The View Report window opens at a width that is narrower than the report it contains. | ~ | ~ | enlarged window /C#/ | Innovation 873 | 1
#69 | Usability | Saving a “permanent” filter blows away a “temporary” one. | ~ | ~ | Isn't that normal? | Innovation 873 | 2
#70 | Usability | Columns can be reordered by user – but no way to revert to original order via GUI. | ~ | ~ | very low pri | Innovation 873 | 3
#71 | Completed | Make final KIDS package | ~ | ~ | MAG3_0I873.KID includes Slide INFO addition with new RPC definition, but legally cannot include field length set longer (120) then 2-75 for field SPECIMEN in SPECIMEN SUB-FIELD in SURGICAL PATHOLOGY SUB-FIELD in file LAB DATA) --> made a release note item & notify LAB Package | Innovation 873 | 1
#72 | Deferred to 105 ( E ) | Make Vendor choice configurable | ~ | (in extension period) - new tab in config menu? - Y - WSI only or voice too? - both - one WSI vendor per site? -- NO! - one voice vendor per site? |  | Innovation 873 | 1
#73 | Deferred | Use scripts for vendors to avoid code changes? | ~ | probably Yes. | Find solution after analyzing the Vendor scripts | Innovation 873 | 1
#74 | Completed | On Consult site, for a remote consult request, where the case's status is Pending Verification, allow the consult dialog to come up with the decline option clickable | ~ | ~ | ConsultationStatusViewModel.cs and MainWindow.xaml.cs is altered; Also prevented duplicate items on consult dialog listbox /C#/ | Innovation 873 | 1
#75 | Completed | Install Aperio ImageScope application and create a file association to run it on "executing" a .sis (aperio config) file | ~ | ~ | Document in Installation Guide the need to install Aperio before WL manger install and use registry setting in installer to associate .sis type to ImageScope | Innovation 873 | 1
#76 | Completed | Installer issues: MS VC++ 2010 redistrubutables fail to install... (if already there) | ~ | ~ | Removed redistributable installation from installer, see #43 (resolved) | Innovation 873 | 1
#77 | Completed | Set "host.port" registry after installation | ~ | ~ | Place a note in install guide for Local VistA broker Server (host, port) configuration after install scripts ran! assumingig host is set in Windows\system32\etc\Hosts file or DNS | Innovation 873 | 1
#78 | Completed | Make mini VIX installer for TP on top of P138 VIX |  |  | drop in PathologyWepApp with mini installShield; Also updated the VIX P138 SoftwareVersion in ViXConfig.xml to 30.138.873.x | Innovation 873 | 1
#79 | Usability | on Closing Consultation dialog Item briefly disappears from the list, then it comes back on refresh |  |  |  | Innovation 873 | 2
#80 | Usability | If the WL Manager application started a Viewer it remebers to erase context on or kill the Viewer, However if the user exits the Viewer app., the WL Manager should check if the Viewer is running, before popping up the viewer with empty content on context change. |  |  |  | Innovation 874 | 3
9/15/15-11/14/15 Extension Period
#101 (A) | Open | Use of PDX for consult site Patient's auto registration if not registered yet (Larry Carlson: contact VA identity Mgmt to make sure auto registration is ok) | ~ |  |  | Innovation 873 | 1
#102 (B) | Open | Automatically accession specimens at the consulting site when a Supplementary Report is verified (SR on top of a verified Main Report) | ~ |  |  | Innovation 873 | 1
#103 ( C ) | Open | Automatic generation of the consulting site report based on the verified supplementary report | ~ |  |  | Innovation 873 | 1
#104 (D) | Open | Automatic encounter generation at the consulting site for workload | ~ |  |  | Innovation 873 | 1
#105 ( E ) deferred from #72 & #73 | Open | Make Vendor choice configurable (If time permits) | ~ | (in extension period) - new tab in config menu? - Y - WSI only or voice too? - both - one WSI vendor per site? -- NO! - one voice vendor per site? |  | Innovation 873 | 1